INSPECTION AND TEST PLAN (ITP)

| PROJECT INFORMATION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Name | Kalgoorlie Airport Hotel (CDI 6425) | Location | 10 Gatacre Drive, Somerville WA 6430 | Scope Overview | Concrete on Ground - pad & strip footings, slabs on ground, thickenings, lift & sump pits, crossovers, footpaths and kerbs (Building 1, Buildings 2 & 3 footings, External Works) |
| Subcontractor | Kooboolong Services Pty Ltd | Trade Package | Concrete |  |
| ITP Ref. | 6425-KBS-ITP-002 | Revision | B | Date | 23/09/2026 |
| Lot/Location | Building 1 / Buildings 2 & 3 / External Works (nominate per lot on the ITR) |  |  |  |  |

| CDI GROUP APPROVAL |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CDI Approval | Name |  | Position | ☐ PM | ☐ SM | ☐ Other (specify) | Signature |  | Date |
| Initial |  |  |  |  |  |

| REFERENCE DOCUMENTATION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Specifications and Drawings |  | Referenced Standards |  | Associated ITR Inspection Numbers |  |
| Specification Number | Specification Title | Standard Reference | Standard Title | ITR Reference | ITR Title |
| DWG: S001_B1 / S002_B1 | Structural General Notes 1 & 2 - Building 1 | AS 3600 (2018) | Concrete structures | 6425-KBS-ITR-002 | Concrete Lot Record (pre-pour and post-pour inspection) |
| DWG: S011_B1 | Standard Details - Footings & Slab on Ground | AS 3610.1 (2018) / 3610.2 (2023) | Formwork for concrete | 6425-KBS-ITR-002A | Concrete Pour Register (dockets, tests, results) |
| DWG: S100_B1 / S300_B1 | Ground Floor & Footing Plan / Sections - Building 1 | AS/NZS 4671 (2019) | Steel reinforcing materials | 6425-KBS-ITR-001 | Earthworks Lot Record (founding inspection) |
| DWG: S001 / S002 | Index & General Notes 1 & 2 - Buildings 2 & 3 | AS 1379 (2007) | Specification and supply of concrete | 6425-KBS-ITP-001 | Earthworks ITP (subgrade & fill) |
| DWG: S090 / S095 / S100 / S200 | Excavation & Batter Plan, Footing Plans, Sections - Buildings 2 & 3 | AS 3798 | Methods of testing soils for engineering purposes |  |  |
| DWG: STR-DRG-000002 / 101010 | SIBS General Structural Notes / Foundation Assemblies Framing Plan | AS 1289 | Admixtures, cement, SCMs |  |  |
| DWG: C-001 / C-002 / C-003 / C-010 / C-011 | Civil General Arrangement, Drainage & Grading, Bulk Earthworks, Details | AS 1012.13 (2015) | Plywood - formwork |  |  |
| Specification CSP | Civil Services Specification | AS 6669 (2016) | Bar chairs and spacers |  |  |
| Specification REP_GEO | Geotechnical Report |  |  |  |  |
| NATSPEC 0311 | Concrete Formwork (Gatacre Drive, Kalgoorlie) |  |  |  |  |
| NATSPEC 0312 | Concrete Reinforcement |  |  |  |  |

Type of Inspection:  H = HOLD (work shall not proceed past this point without verified acceptance)   W = WITNESS (nominee notified and invited; work may proceed)   R = REVIEW (verification by documentary evidence)

| No. | Description of required activity | Governing specification or standard | Acceptance Criteria | Record of compliance / completion | Kooboolong | CDI | Engineer |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GENERAL |  |  |  |  |  |  |  |
| 1. | - Review SOW, SWMS, drawings and specifications | - LOI 6425-COM-SC-LOI-002 Att. 2 - Structural general notes | - Contract scope, exclusions and clarifications confirmed - Current IFC revision of all structural and civil drawings confirmed on Procore - Approved SWMS for formwork, steel fixing, concrete placement - Concrete grades, exposure classes, cover and finish classes taken from drawings / general notes - Inspection notice periods: 24 h notice | - Prior to works commencing - Document review record | H, R | H, R |  |
| 2. | - Submissions | - 0314 - 0311 | - Concrete: placing, compaction and finishing method incl. pumping; sequence and times of placement and construction joint locations; hot / cold weather temperature control; sawn joint method, timing and sequence; curing and protection methodology (0314 cl. 3.8: contractor to submit for review) - Reinforcement: type test reports (AS 3600 Table 3.2.1); any proposed change, site bend, splice or mechanical splice | - CDI / Engineer review | H | R | R |
| 3. | - Approved concrete mix designs | - AS 1379 (2007) cl. 1.5.3 / 1.5.4 - AS 3600 (2018) | - Normal-class or special-class mix submitted for each grade and exposure class on the drawings - Properties as documented: strength grade, slump, max aggregate, cement to AS 3972 - Hot-weather retarder / measures nominated so delivered concrete stays within 5-35 C | - Mix design certificates - Engineer approval | H | R | H |
| 4. | - Reinforcement compliance | - AS/NZS 4671 (2019) - AS 3600 (2018) cl. 17.2 - 0312 cl. 2.1 | - Surfaces free of loose or flaking scale and rust, oil, grease and mud; stored above ground and protected - CDI free-issue reinforcement (Buildings 2 & 3): condition, tags and quantities checked against schedule within 24 h of delivery; discrepancies notified in writing with photos - Tie wire annealed steel min 1.25 mm | - Delivery dockets - Delivery check record | H | R |  |
| EXCAVATION & FOUNDATION |  |  |  |  |  |  |  |
| 5. | - Detailed excavation and foundation inspection | - Geotechnical Report - Structural general notes - Earthworks ITP 6425-KBS-ITP-001 | - Excavation to RL and dimensions shown; sides stable, base clean, no loose, soft, wet or contaminated material - Founding material inspected and approved by geotechnical / structural engineer at every pad, strip and pit before blinding, membrane or reinforcement (inspection of base / subgrade before covering) - Unsuitable material: stop, notify CDI, Engineer direction obtained | - Earthworks Lot Record 6425-KBS-ITR-001 (HP2) - Engineer sign-off - Photos | H | W | H |
| 6. | - Subgrade / fill under slabs on ground | - Earthworks ITP 6425-KBS-ITP-001 - AS 3798 / AS 1289 - Geotechnical Report | - Compaction test results for all fill layers passed and closed under the Earthworks ITP - Services trenches by others backfilled and as-constructed received before slab preparation | - Test Register 6425-KBS-ITR-001A | H | W | R |
| FORMWORK & REINFORCEMENT |  |  |  |  |  |  |  |
| 7. | - Formwork | - AS 3610.1 (2018) / AS 3610.2 (2023) - 0311 cl. 1.6, 3.1 - AS 3600 cl. 17.5 | - Position so finished concrete conforms to AS 3600 - Plywood to AS 6669, grade to suit loading and finish; forms clean and free of dust and debris before concrete - Release agent applied before reinforcement is placed, thin uniform film, surplus removed - Formwork inspected (cleaned, debris removed) | - Concrete Lot Record 6425-KBS-ITR-002 (section B) - Photos | H | W |  |
| 8. | - Reinforcement fixing | - AS 3600 (2018) cl. 17.2.5, 17.5.3, 4.10 - AS/NZS 4671 (2019) - 0312 cl. 3.1 | - Bar size, grade, spacing, laps and splices to drawings; position tolerance to AS 3600; cover as documented to AS 3600 - Ties at every intersection on beams/footing cages (each stirrup corner; other bars at 1 m max) and at alternate intersections on mats; tie ends bent away from the cover zone - Site bending only to AS 3600, no heat; every projecting starter capped - Reinforcement clean of loose rust, oil, mud and release agent | - Concrete Lot Record 6425-KBS-ITR-002 (section D) - Photos | H | W | H |
| PRE-POUR |  |  |  |  |  |  |  |
| 9. | - Pre-pour inspection | - KBS Pre-Pour Checklist - 0314 cl. 1.6 / 0312 cl. 1.6 / 0311 cl. 1.8 | - Checklist completed and issued to CDI 24h before pour; all items closed or accepted - Engineer inspection of reinforcement; KBS supervisor present; all items closed - Concrete booked (grade, volume, truck spacing ), pump, tester and finishers confirmed; access, washout, lighting, evaporation barriers, curing materials on site - HOLD POINT - no concrete ordered for delivery until approved by CDI | - Concrete Lot Record 6425-KBS-ITR-002 HP1 signed - DCI release | H | H | H |
| CONCRETE PLACEMENT |  |  |  |  |  |  |  |
| 10. | - Concrete delivery and acceptance | - AS 1379 (2007) cl. 4.2.3 - 0314 cl. 1.5, 3.2 | - Every docket checked and retained: Information plus element placed, water added at plant and maximum permitted on site, delivery supervisor name, placement method - Concrete temperature at discharge between 5 and 35 C; no discharge at ambient below 10 C or above 30 C unless approved heating / cooling measures are in place - Maximum elapsed time from wetting to discharge: 5-24 C = 120 min; 24-27 C = 90 min; 27-30 C = 60 min; 30-35 C = 45 min | - Pour Register 6425-KBS-ITR-002A - Delivery dockets - Temperature / slump record | W | R | W |
| 11. | - Concrete sampling and testing | - AS 1012.1 (2014), 1012.3.1, 1012.8.1, 1012.9 (2014) - AS 1379 (2007) Sections 5 & 6 - 0314 | - NATA-accredited testing; project assessment; slump test on every batch at the point of discharge from the agitator - Compressive strength samples per grade per day spread evenly through the pour - Results kept on site; issued to CDI within 2 business days of receipt; 7 and 28 day results on the Pour Register; low results notified to Engineer immediately | - NATA test reports - Pour Register 6425-KBS-ITR-002A | W | R | W |
| 12. | - Placing, compacting and finishing | - AS 3600 (2018) - 0314 - 0315 Concrete finishes [not received] - Approved SWMS | - Compaction by vibrators; vibrators not to touch set concrete, reinforcement or embedded items and not used to move concrete - Placing logbook kept on site for every placement: date, grade and source, slump, portion of work, volume - Finish class to drawings; levels and falls to drawings; surface protection | - Placing logbook / Pour Register - Photos - Level check | W | W |  |
| 13. | - Joints and saw cuts | - 0314 cl. 3.7 - IFC drawings | - Construction joints only where documented; - Control joints in slabs on ground: tooled or sawn, 3-5 mm wide, depth 0.25-0.33 x slab depth, formed as early as the concrete will take the saw without dislodging aggregate (same day in heat) - Expansion / isolation joints: dowels located and aligned per drawings and held during placement; joint surfaces dry, clean and primed; non-adhering backing rod; filler and sealant as documented, finished flush; watertight where subject to water | - Joint layout record - Photos | W | R |  |
| 14. | - Curing and protection | - AS 3600 (2018) - AS 3799 (1998) - 0314 | - Curing continuous from completion of finishing once the surface will not be damaged; method per the submitted and reviewed curing methodology - Formwork stripped before the curing period ends: curing of exposed faces continued within one hour of exposure | - Pour Register (curing method, start time) - Photos | W | R |  |
| POST-POUR |  |  |  |  |  |  |  |
| 15. | - Post-pour inspection | - AS 3600 (2018) cl. 17.5 | - Surface finish, edges, joints and rebates conform; defects (honeycombing, cracking, bleed, blowholes, spalls) identified and recorded - Any make-good required before internal walls / modules identified and scheduled | - Concrete Lot Record 6425-KBS-ITR-002 (section H) - Level survey - Photos | H | W | R |
| 16. | - Concrete repairs and defects | - 0314 cl. 1.5 (cutting / coring submissions) - Engineer direction - Approved SWMS | - Repair method for any structural defect, and any cutting or coring of hardened concrete, submitted and approved by Engineer before work; proprietary repair materials to manufacturer's data - Defects notified by CDI rectified within 48 hours of notice or as agreed - Repairs recorded with photos before and after | - Defect record - Photos - Engineer approval | H | R | H |
| 17. | - Concrete strength results | - AS 1012.9 (2014) - AS 1379 (2007) project assessment - 0314 cl. 3.3 | - 28-day results meet characteristic strength per AS 1379 project assessment; results logged against pour and element - Non-conformance: Engineer notified immediately; NCR raised; investigation (core testing) and disposition per Engineer direction | - NATA reports - Pour Register - NCR register | R | R | H |
| COMPLETION |  |  |  |  |  |  |  |
| 18. | - Final inspection / handover | - IFC drawings - This ITP | - All pours complete, all defects rectified and NCRs closed - Pour Register and placing logbook complete: every pour cross-referenced to dockets, mix, slump, temperature, cylinders and 7/28 day results - As-constructed information provided (survey responsibility as agreed in the Subcontract) - Founding inspection records, pre- and post-pour ITRs, test reports and this ITP signed and issued to CDI | - Signed ITP - ITRs 6425-KBS-ITR-001, 001A, 002, 002A - Pour Register - NCR register | H | H | R |

ITP Comments and Notes:

Works completed and testing completed in line with this ITP except as noted above.

| Reviewed and accepted by: | Concrete on Ground - Kooboolong Services | CDI Group |
| --- | --- | --- |
| Name: | Mitchell van Zyl |  |
| Position/Title: | Project Manager |  |
| Date: |  |  |
| Signature: |  |  |