INSPECTION AND TEST PLAN (ITP)

| PROJECT INFORMATION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Name | Curtin B316 Sciences Project | Location | Curtin University, Brand Drive & Hayman rd, Bentley, Western Australia | Scope Overview | Soft Landscaping - Garden Beds (GA01, GA02, GA03), Tree Planting & Turf (TU01) |
| Subcontractor | Kooboolong Services | Trade Package | Soft Landscaping |  |  |
| ITP Ref. | KBS_C001_ITP_002 | Revision | A | Date | 25/08/2026 |
| Lot/Location |  |  |  |  |  |

| LENDLEASE APPROVAL |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lendlease Approval | Name |  | Position | PM | SM | Other (specify) | Signature |  | Date |  |
|  |  |  | Initial |  |  |  |  |  |  |  |

| REFERENCE DOCUMENTATION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Specifications and Drawings |  | Referenced Standards |  | Associated Checklists or Inspection Reports |  |
| Specification Number | Specification Title | Standard Reference | Standard Title | Checklist Reference | Checklist Title |
| 01SITE-L-00-GN0001 | Legends, Abbreviation & Code | AS 4419 | Soils for landscaping and garden use | CL-01 | Soil, Mulch & Material Approval Record |
| 01SITE-L-00-GN0002 | Planting Schedule | AS 4454 | Composts, soil conditioners and mulches | CL-02 | Nursery Stock Inspection / Tagging Record |
| 01SITE-L-00-GN0011 | Planter Bed Qty Schedule - Threshold C | AS 2303 | Tree stock for landscape use | CL-03 | Garden Bed Setout & Levels Check |
| 01SITE-L-00-GN0012 | Planter Bed Qty Schedule - Busport & East Gate | AS 4373 | Pruning of amenity trees | CL-04 | Pre-Mulch Irrigation Commissioning Record |
| 01SITE-L-00-GN0014 | Planter Bed Qty Schedule - B316 External | AS 4970 | Protection of trees on development sites | CL-05 | Practical Completion Inspection & Defects List |
| 01SITE-L-60-PL0001 | Threshold C Planting Plan | AS 3743 | Potting mixes |  |  |
| 01SITE-L-60-PL0002 | East Gate & Plaza Planting Plan | AS 1289 | Methods of testing soils for engineering purposes |  |  |
| 01SITE-L-60-PL0003 | Brand Drive South Planting Plan |  |  |  |  |
| 01SITE-L-60-PL0004 | B316 External Planting Plan |  |  |  |  |
| 01SITE-L-60-PL0005 | East Gate Planting Plan |  |  |  |  |
| 01SITE-L-90-DT0098 | Details - Softworks Typical Details |  |  |  |  |
| TBC | Landscape Softworks Specification |  |  |  |  |

|  | Description of required activity | Governing specification or standard | Acceptance Criteria | Record of compliance/ completion |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Type of Inspection H = HOLD W = WITNESS R = REVIEW |  |  |  |
|  |  |  |  |  | Kooboolong | Lendlease | WSP | Aspect |
| GENERAL |  |  |  |  |  |  |  |  |
| 1. | - Review SOW, SWMS, drawings and associated Specifications. | - Contract & SOW | - Contractual accepted specifications & Approved SWMS - Current IFC revision of all landscape drawings confirmed - Planting Schedule and Planter Bed Qty Schedules reconciled against planting plans | - Prior to works commencing | H, R | H, R |  |  |
| 2. | - Subgrade / substrate handover (by others) | - 01SITE-L-90-DT0098 - AS 3798 - AS 4419 | - Garden Beds on Grade (GA01 / GA02) & Turf (TU01) - Existing subgrade trimmed to levels permitting the full specified soil profile depth - Surface free of builders rubble, rock, contamination, weeds and standing water - Compacted subgrade ripped / scarified to allow free drainage - Garden Beds on Structure (GA03) - Structural slab laid to falls, waterproof membrane, drainage and drainage penetrations complete and signed off by others - WPM flood / leak test complete and accepted prior to landscape works - Inspection point and drainage locations confirmed against hydraulic documentation | - Handover Record - WPM Leak Test Certificate (by others) - Photos | H | H | R | R |
| 3. | - Set out | - 01SITE-L-60-PL0001 - PL0005 - 01SITE-L-00-GN0001 - 01SITE-L-00-GN0011 / 0012 / 0014 | - Garden bed extents, bed types (GA01 / GA02 / GA03), turf areas and tree locations set out to planting plans - Bed edges true to line and matched to adjacent hardscape - Tree positions confirmed clear of services, pits, footings and lighting - Existing trees to be retained protected in accordance with AS 4970 - Any conflicts with as-built hardscape raised as an RFI prior to excavation | - Setout Record - Services Location / DBYD - Photos | W | W | R |  |
| MATERIALS |  |  |  |  |  |  |  |  |
| 4. | - Soil, Soil Improver & Lightweight Soil Mix | - AS 4419 - AS 4454 - 01SITE-L-90-DT0098 - Landscape Specification | - Soil analysis report supplied for each soil type (pH, EC, nutrient, texture, organic matter) - Site topsoil free of rocks, rubble, rubbish, weeds, roots and contaminants - Soil improver complies with AS 4454 and is fully matured / composted - Lightweight soil mix (GA03) to specified mix design and free-draining - Samples submitted and approved prior to bulk delivery - No substitution without written approval | - Material Certificate - Sample Approval - Delivery Dockets | H | R |  | H |
| 5. | - Mulch | - AS 4454 - 01SITE-L-90-DT0098 - 01SITE-L-00-GN0001 | - Organic mulch complies with AS 4454, free of weed seed, pathogens and contaminants - Rock mulch to type, size and colour nominated in the Material Schedule - Mulch type confirmed against bed type on the planting plans (organic vs rock) - Sample submitted and approved prior to bulk delivery | - Material Certificate - Sample Approval - Delivery Dockets | H | R |  | H |
| 6. | - Plant Stock | - AS 2303 - 01SITE-L-00-GN0002 - 01SITE-L-00-GN0011 / 0012 / 0014 | - Species, pot sizes and quantities as scheduled - no substitution without written approval - Stock true to name and labelled - Trees comply with AS 2303 - correct height / calliper ratio, single dominant leader, balanced canopy - Root systems well established, no root circling, girdling or pot bound stock - Free of pest, disease, physical damage and weed contamination - Nursery inspection and tagging undertaken prior to delivery - Stock protected, shaded and watered on site pending planting | - Nursery Inspection Record - Delivery Dockets - Photos | H | H |  | H |

| MATERIALS (CONT.) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 7. | - Ancillary Materials | - 01SITE-L-90-DT0098 - 01SITE-L-00-GN0001 - Manufacturer Specification | - Drainage cell, geofabric and root anchor system as specified - Tree stakes and proprietary tree ties as specified - Garden edge EDS01 - 5mm THK x 150mm H galvanised steel with 300 x 50EA3 stakes @ 600 c/c - Manufacturer technical data sheets and installation instructions provided | - Material Certificate - Technical Data Sheets - Delivery Dockets | W | R |  |  |
| SOIL PROFILE & BED CONSTRUCTION |  |  |  |  |  |  |  |  |
| 8. | - Soil Placement | - 01SITE-L-90-DT0098 - AS 4419 | - GA01 / GA02 - Beds on Natural Ground - 200mm soil improver rotary hoed into 300mm site topsoil - GA03 - Beds on Structure - Lightweight soil mix minimum 300mm depth (450mm nominal bed depth) - Minimum 1000mm lightweight soil mix depth at tree locations - TU01 - Turf Areas - 100mm soil improver rotary hoed into 100mm site topsoil - General - Soil placed in even layers and lightly consolidated - no over-compaction or trafficking when wet - No rocks, rubble, rubbish or foreign material within the profile - Finished soil level set to achieve mulch / turf level 25mm below surrounding hardscape typical - Beds graded evenly with no depressions, ponding or high spots | - Depth Check Records - Survey / Level Check - Photos | W | W |  | W |
| 9. | - Bed Profiling, Basins & Edging | - 01SITE-L-90-DT0098 - 01SITE-L-00-GN0001 - 01SITE-L-60-PL0001 - PL0005 | - GA02 - Basin Garden Bed - Batters graded at maximum 1:3 slope - Minimum 600mm flat zone maintained at base of basin - Mulch / soil berm formed as detailed - Mortared rock pitching installed to pit surround - Overflow pit set to level per civil documentation - no obstruction to inlet - Edging - Garden edge installed true to line and level, stakes at 600 c/c, top edge flush with adjacent finished levels | - Survey / Level Check - Photos | W | W | R | W |
| PLANTING & TURF |  |  |  |  |  |  |  |  |
| 10. | - Tree Planting | - 01SITE-L-90-DT0098 - AS 2303 - AS 4373 - 01SITE-L-00-GN0002 | - Planting hole provides minimum 300mm clearance around the root ball - Base of hole filled with existing site soil and soil improver as specified, free of rocks, rubble and rubbish - Tree set plumb with root flare at finished soil level - not planted proud or buried - Backfill with topsoil lightly compacted in 150mm layers, no air voids - Root anchor system installed to manufacturer specification where detailed - Trees under 500L - 3 no. proprietary tree ties in figure of 8 configuration placed at one third height of tree from ground - Stakes neatly cut off level 200mm above tree ties post installation - Ties firm but not restricting or damaging the trunk - Mulch / soil berm formed around the tree - Trees on structure - minimum 1000mm soil depth confirmed at tree location - Tree watered in immediately after planting - HOLD POINT - first tree pit of each type to be inspected prior to bulk planting | - Pre-Plant Inspection - Photos - Delivery Dockets | H | H |  | H |
| 11. | - Shrub & Groundcover Planting | - 01SITE-L-00-GN0002 - 01SITE-L-00-GN0011 / 0012 / 0014 - 01SITE-L-60-PL0001 - PL0005 | - Species, pot size and planting rate (per m2) as scheduled for each bed - Meadow mixes set out to the scheduled proportion of mix and randomly distributed - no obvious rows or clumping - Quantities reconciled against the Planter Bed Qty Schedules for each bed - Plants watered thoroughly prior to planting - Root balls teased where required, plants set at correct depth with top of root ball flush with finished soil level - Holes backfilled and firmed with no air voids - Plants set out clear of bed edges, hardscape and services to allow for mature spread - Planted areas watered in immediately after planting | - Plant Count Record - Setout - Approval - Photos | W | W |  | H |
| 12. | - Turf (TU01) | - 01SITE-L-90-DT0098 - AS 4419 | - Turf supplied fresh, laid within 24 hours of delivery, kept moist prior to laying - Prepared soil graded smooth, even and free of stones and debris - Turf laid with staggered close butt joints - no gaps, overlaps or exposed soil - Turf rolled / tamped to ensure full contact with the soil profile - Finished turf level flush with adjacent hardscape and edging - Turf watered thoroughly immediately after laying - No trafficking of newly laid turf | - Delivery Dockets - Photos | W | W |  | W |
| 13. | - Mulching | - 01SITE-L-90-DT0098 - AS 4454 | - Irrigation complete, pressure tested and commissioned prior to mulching - Mulch placed to 75mm minimum depth, uniform across the bed - Mulch kept clear of and sloped toward the base of plant stems - Raked to an even surface flush with the surrounding design levels - Mulch level 25mm below surrounding hardscape typical | - Depth Check - Photos | W | W |  | W |
| COMPLETION |  |  |  |  |  |  |  |  |
| 14. | - Irrigation Interface & Commissioning | - Irrigation Drawings - 01SITE-L-90-DT0098 | - Irrigation installed, pressure tested and commissioned in accordance with the irrigation documentation / ITP - Drippers / emitters located at plant positions and not displaced during mulching - Controller programmed and watering schedule handed over - No leaks, weeping or damage to the system following mulching | - Commissioning Record - Pressure Test Record - As-Built Marked Up | W | H |  | R |
| 15. | - Final Inspection / Practical Completion | - 01SITE-L-00-GN0002 - 01SITE-L-60-PL0001 - PL0005 - 01SITE-L-90-DT0098 | - Plant species, pot sizes and quantities verified against the Planting Schedule and Planter Bed Qty Schedules - All plants healthy, plumb, firm in the ground and free of damage, pest and disease - No gaps, bare patches or missed areas within beds - Mulch depth, type and finished levels uniform throughout and 25mm below adjacent hardscape - Beds free of weeds, rubbish, debris and construction spoil - Bed edging true to line and level with no damage - No ponding within beds, basins or turf areas - Turf knitted, evenly laid, flush with adjacent surfaces and free of gaps - Trees plumb, securely staked / anchored, ties correctly fitted and not causing damage - Irrigation operational across the full works area - Surrounding hardscape cleaned down and free of soil and mulch staining | - Practical Completion Inspection - Defects List - Photos - Plant Count Record | H | H | H | H |

| Reviewed and accepted by: | Soft Landscaping - Kooboolong Services | Lendlease |
| --- | --- | --- |
| Name: |  |  |
| Position/Title: |  |  |
| Date: |  |  |
| Signature: |  |  |